ArchLens

50-Day Scrum Implementation & Dataset Plan

Multimodal AI for Software Architecture Conformance Checking and Root-Cause Analysis

# 1. Project Overview

ArchLens is a multimodal software-engineering research system that combines Computer Vision, Vision-Language Models (VLMs), Large Language Models (LLMs), static source-code analysis, dependency graphs and Git evidence to compare intended software architecture with implemented architecture, detect architectural violations, identify likely root causes, estimate impact and generate evidence-grounded corrective recommendations.

| Item | Plan |
| --- | --- |
| Duration | 50 days |
| Team | 4 members |
| Structure | 10 sprints × 5 days |
| Core modalities | Architecture diagrams + source code + Git history + LLM/VLM reasoning |
| Primary research output | Conformance benchmark, reproducible pipeline, evaluation and research artifact |
| Important design rule | Deterministic structural facts are established by analysis tools; LLMs support semantic reasoning. |

# 2. System Scope

The implementation is organized into eight interconnected modules:

| Module | Name | Main responsibility |
| --- | --- | --- |
| M1 | Dataset & Benchmark | Collect/normalize repositories, diagrams and ground truth; create controlled architecture violations. |
| M2 | Computer Vision Pipeline | Preprocess diagrams; detect components/connectors; segment relevant regions. |
| M3 | Architecture/VLM Semantic Extraction | Use ViT/VLM/CLIP-style methods and structured prompting to infer component semantics and relationships. |
| M4 | Source-Code Architecture Recovery | Recover packages, classes, imports, calls, inheritance and dependency graphs using static analysis. |
| M5 | Graph & Conformance Engine | Construct intended/current graphs and apply explicit conformance rules. |
| M6 | Git Evidence + LLM RCA | Use commits, diffs, blame and dependency history to identify likely root causes. |
| M7 | Impact Analysis + Recommendations | Traverse affected dependencies and generate evidence-grounded corrective recommendations. |
| M8 | Evaluation, Dashboard & Research Artifact | Run baselines/ablations, error analysis, metrics, documentation and demo. |

# 3. Team Division of Work

No member owns an entire module. Each member participates in multiple modules throughout the 50 days, so everyone gets practical exposure to CV, LLM/VLM, source analysis, graph reasoning, evaluation and integration.

| Member | Primary role | Primary contributions | Cross-training |
| --- | --- | --- | --- |
| P1 | CV / Vision Lead | CV preprocessing, object/component detection, ViT baseline, geometry and CV evaluation | LLM prompting, RCA evaluation |
| P2 | LLM / VLM Lead | VLM prompting, semantic extraction, CLIP/few-shot experiments, LLM gateway | CV annotation/detection, graph validation |
| P3 | Static Analysis / Graph Lead | AST/dependency extraction, graph construction, conformance rules, history analysis | CV baselines, LLM evidence validation |
| P4 | Backend / Integration Lead | Repository ingestion, APIs, JSON schemas, integration, UI/visualization | CV evaluation, RCA packaging, experiment management |

# 4. Sprint Plan — 10 Sprints × 5 Days

## Sprint 1 — Days 1–5

Focus: Foundation, dataset and architecture

P1: Define CV pipeline and diagram representation.

P2: Define LLM/VLM interface and structured outputs.

P3: Define architecture graph, dependency schema and conformance model.

P4: Define backend interfaces, repository ingestion and experiment structure.

All: finalize datasets, annotation format, Git workflow, API contracts and baseline protocol.

## Sprint 2 — Days 6–10

Focus: CV preprocessing + source-code ingestion

P1: image resizing, normalization and preprocessing pipeline.

P2: denoising/contrast enhancement and diagram annotation workflow.

P3: Canny/LoG/DoG edge baselines and Java/static parser experiments.

P4: morphology experiments and repository ingestion.

All: establish Python AST/Tree-sitter/JavaParser outputs in a common schema.

## Sprint 3 — Days 11–15

Focus: Component detection + architecture recovery

P1: YOLO/component-detection baseline.

P2: annotation quality and detection experiments.

P3: Faster R-CNN or comparable detection baseline; calls/inheritance extraction.

P4: detection evaluation and source-repository pipeline.

All: extract classes/packages/imports/calls/inheritance and construct first dependency graphs.

## Sprint 4 — Days 16–20

Focus: Segmentation + architecture graph

P1: U-Net/segmentation baseline.

P2: component-mask generation and validation.

P3: connector/edge segmentation and graph confidence representation.

P4: JSON-to-graph pipeline and graph visualization.

All: define component and relationship schemas and intended/current graph formats.

## Sprint 5 — Days 21–25

Focus: VLM, ViT, CLIP and relationship extraction

P1: ViT image-understanding baseline and geometry-based relation extraction.

P2: VLM structured prompting and semantic component classification.

P3: CLIP zero-shot baseline and edge/Hough reasoning.

P4: few-shot prompting and integrated extraction evaluation.

All: compare direct VLM, CV-only, geometry-assisted and hybrid extraction.

## Sprint 6 — Days 26–30

Focus: Intended vs current architecture + conformance

P1: implement explicit conformance rules.

P2: graph matching and semantic alignment.

P3: violation classification and confidence handling.

P4: conformance API, test cases and report generation.

All: support CONFORMANT, VIOLATION, MISSING, UNEXPECTED and UNCERTAIN outcomes.

## Sprint 7 — Days 31–35

Focus: Git evidence + LLM root-cause analysis

P1: commit extraction and candidate-commit retrieval.

P2: diff/message processing and LLM reasoning prompts.

P3: blame/dependency-history analysis and evidence validation.

P4: evidence-package construction and LLM gateway.

All: ensure RCA is evidence-grounded and compare LLM-only vs evidence-grounded reasoning.

## Sprint 8 — Days 36–40

Focus: Impact analysis + corrective recommendations

P1: dependency traversal and architecture-aware recommendations.

P2: LLM impact reasoning and recommendation generation.

P3: affected-node detection and rule validation.

P4: impact visualization and recommendation interface.

All: integrate end-to-end flow from diagram/code to violation, RCA, impact and recommendation.

## Sprint 9 — Days 41–45

Focus: Evaluation, baselines and ablations

CV: YOLO vs ViT/VLM vs CLIP vs hybrid.

Architecture extraction: VLM-only vs CV-only vs CV+VLM vs CV+VLM+geometry.

Conformance: LLM-only vs static-only vs VLM-only vs static+LLM vs ArchLens.

RCA: LLM without Git vs +Git vs +Git+dependency graph.

Run repeated trials, collect metrics, confidence intervals where appropriate and detailed error analysis.

## Sprint 10 — Days 46–50

Focus: Final integration, paper and demo

P1: final CV evaluation and figures.

P2: final LLM/VLM experiments and prompt/model analysis.

P3: graph/conformance validation and reproducibility package.

P4: final dashboard/demo/API packaging.

All: finalize benchmark, results, limitations, research paper, documentation and live demonstration.

# 5. 50-Day Milestone Roadmap

| Day | Milestone |
| --- | --- |
| Day 5 | Dataset, schemas, system architecture and development environment |
| Day 10 | CV preprocessing + source-code ingestion working |
| Day 15 | Component detection + dependency extraction |
| Day 20 | Segmentation + first architecture graphs |
| Day 25 | VLM/ViT/CLIP semantic extraction |
| Day 30 | Intended/current graph comparison + conformance engine |
| Day 35 | Violation detection + Git evidence + first RCA |
| Day 40 | Impact analysis + corrective recommendations |
| Day 45 | Baselines, ablations and evaluation |
| Day 50 | Integrated system + benchmark + paper + demo |

# 6. Scrum Structure

## 6.1 Sprint cadence

Each sprint lasts five days. Sprint Planning defines the sprint goal and task allocation. A short daily stand-up tracks progress, blockers and cross-member dependencies. At the end of each sprint, the team performs a Sprint Review using a working artifact, followed by a retrospective.

| Ceremony | Frequency | Purpose |
| --- | --- | --- |
| Daily stand-up | Daily, ~15 min | Yesterday / today / blocker |
| Sprint planning | Every 5 days | Select and distribute stories |
| Sprint review | Every 5 days | Demonstrate working increment |
| Retrospective | Every 5 days | Identify process improvements |
| Research sync | 2× per week | Review experimental validity and paper evidence |

## 6.2 Definition of Done

Code is implemented, tested and merged into the shared repository.

Experiment has a defined dataset split, baseline, metric and reproducible result.

Outputs conform to the shared JSON/graph schema.

Research claims are supported by measured results rather than assumptions.

Known limitations and failure cases are documented.

Integrated APIs/pipelines are tested with representative inputs.

Each sprint produces a demonstrable increment.

# 7. Product Backlog

| Stories | Epic | Scope |
| --- | --- | --- |
| US1–US5 | Dataset | Repository/diagram collection, normalization, annotation, ground truth, controlled violations |
| US6–US13 | Computer Vision | Preprocessing, detection, segmentation, ViT, CLIP, geometry, evaluation |
| US14–US17 | Architecture Recovery | AST parsing, dependency extraction, semantic abstraction, graph construction |
| US18–US21 | Conformance | Graph alignment, rules, violation classification, report generation |
| US22–US26 | LLM/RCA | Prompting, LLM gateway, evidence packaging, RCA, recommendation generation |
| US27–US32 | Evaluation | Baselines, ablations, metrics, error analysis, reproducibility, final benchmark |

# 8. Dataset Strategy

A single public dataset is unlikely to cover the entire multimodal problem. The recommended approach is to combine complementary public benchmarks and create a small ArchLens-specific conformance benchmark.

| Dataset | What it provides | How ArchLens uses it |
| --- | --- | --- |
| ArchEval Benchmark | 8 curated open-source repositories with repository data, architecture diagrams and architecture documentation. | Primary end-to-end validation. |
| SAR datasets | Software architecture recovery benchmark data including source files, dependency matrices and reference decompositions. | Static architecture recovery and graph validation. |
| StructSAR | Preprocessed dependency graphs and ground-truth architectures for multiple Java/C/C++ systems. | Controlled architecture-recovery experiments. |
| SemArc | Software architecture recovery augmented with semantic analysis; includes ground-truth systems and LLM-based semantic analysis resources. | LLM-assisted architecture abstraction. |
| ArDoCo Benchmark | Traceability links among software architecture documentation, models, code and diagrams. | Traceability evaluation. |
| UML-in-the-Wild | Large collection of PlantUML diagrams with rendered images, source and structural metadata. | Diagram/VLM pretraining or evaluation. |
| Software Architecture Diagram Connectivity dataset | Architecture-diagram connectivity benchmark focused on connectivity/arrowhead understanding by vision-language models. | Relationship/edge extraction evaluation. |
| UML class diagram dataset | Annotated UML class-diagram images with bounding-box-oriented annotations. | Component detection baseline. |
| Multiclass UML diagram dataset | 3,231 images across class, activity, use-case, sequence and non-UML categories. | Diagram classification/pretraining. |
| ArchLens-Conformance (new) | Team-created benchmark containing real repositories plus controlled architecture violations, intended/current graphs, offending edges, commits, root causes and expected corrections. | Main research contribution. |

# 9. Proposed ArchLens-Specific Benchmark

Target scale for a 50-day research prototype:

8–12 real open-source repositories.

50–100 architecture diagrams or diagram variants.

40–80 controlled architecture variants.

100–200 labeled architecture-violation instances.

1,000+ commits examined for candidate root causes.

500–2,000 sampled CV training/validation images where appropriate.

100–300 held-out diagram test images.

Recommended annotation fields:

| Field | Example contents |
| --- | --- |
| Repository | Repository identifier and commit/version |
| Intended graph | Components, relationships, layers and constraints |
| Current graph | Recovered components and dependencies |
| Violation | Type, offending edge/node, source location |
| Evidence | Diagram region, source file, dependency path, commit/diff |
| Root cause | Ground-truth introducing/refactoring commit where available |
| Impact | Affected components/classes/dependencies |
| Expected correction | Architecture-compliant corrective action |

# 10. Evaluation Plan

## 10.1 Core research questions

| RQ | Question |
| --- | --- |
| RQ1 | How accurately can architecture components and relationships be extracted from diagrams using CV/VLM methods? |
| RQ2 | How accurately can intended and implemented architectures be aligned and compared? |
| RQ3 | Does deterministic static analysis combined with LLM semantic reasoning improve conformance detection? |
| RQ4 | Does Git history and dependency evidence improve root-cause localization? |
| RQ5 | Which evidence sources contribute most to violation detection and RCA? |

## 10.2 Metrics

| Task | Metrics |
| --- | --- |
| Component/relationship extraction | Precision, Recall, F1; IoU where bounding boxes/masks are used |
| Architecture recovery | Component matching accuracy; relationship precision/recall/F1 |
| Conformance | Violation precision/recall/F1; false-positive and false-negative analysis |
| RCA | Top-1 and Top-k localization accuracy |
| Recommendation quality | Expert rubric / structured criteria such as correctness, relevance and evidence support |
| Robustness | Repeated LLM trials, model/prompt sensitivity and confidence analysis |

## 10.3 Required baselines and ablations

LLM-only

Static-analysis-only

VLM-only

CV-only

Static + LLM

CV + VLM

CV + VLM + geometry

Full ArchLens: diagram + static analysis + Git + LLM

# 11. Technical Stack

| Layer | Suggested tools |
| --- | --- |
| Computer Vision | OpenCV, PyTorch, YOLO, U-Net, ViT, CLIP/VLM |
| Program analysis | Python AST, Tree-sitter, JavaParser or equivalent parsers |
| Version control analysis | GitPython / Git CLI |
| Graph reasoning | NetworkX; PostgreSQL/graph-oriented storage if required |
| LLM layer | Model/API gateway with structured JSON output, caching, retries and validation |
| Backend | FastAPI |
| Frontend | React |
| Experimentation | pandas, scikit-learn, MLflow or W&B |
| Deployment | Docker |

# 12. Architecture Principle: What the LLM Should and Should Not Decide

ArchLens should use the LLM as a semantic reasoning component rather than as the sole authority for deterministic software facts.

| Question | Preferred mechanism |
| --- | --- |
| Does A import B? | Static analysis |
| Does A depend on B? | Dependency graph |
| Is A → B forbidden by the intended architecture? | Conformance engine |
| Which architecture concept does this component represent? | VLM/LLM semantic reasoning |
| Why was the violation introduced? | Evidence-grounded LLM over Git evidence |
| What is the likely downstream impact? | Graph traversal + LLM reasoning |
| How should the violation be corrected? | Rules + evidence-grounded LLM recommendation |

# 13. Risks and Mitigation

| Risk | Mitigation |
| --- | --- |
| Relationship/edge extraction is harder than component detection | Use geometry, edge detection, structured VLM prompting and graph validation. |
| LLM hallucination | Require evidence packages, structured outputs and deterministic validation. |
| Free-tier/API limits | Cache responses, batch experiments, use open/local models where practical, and maintain a model gateway. |
| Stale architecture diagrams | Record diagram version/commit and treat uncertain or mismatched evidence explicitly. |
| Ground-truth scarcity | Combine public benchmarks with controlled violations and expert-reviewed annotations. |
| 50-day scope pressure | Prioritize the MVP pipeline first; runtime/deployment telemetry remains future scope. |
| Scalability | Filter candidate violations before expensive LLM calls and avoid sending whole repositories. |

# 14. Scope Boundary

The 50-day version should prioritize diagram-to-graph extraction, source-code architecture recovery, formal conformance checking, Git-based root-cause analysis, impact analysis and recommendations. Full runtime/deployment telemetry fusion and continuous production monitoring should be treated as future work unless the MVP stabilizes significantly earlier than expected.

# 15. Final Deliverables by Day 50

Working ArchLens prototype with end-to-end pipeline.

Structured intended and current architecture graphs.

Conformance report with explicit violation categories.

Evidence-grounded Git root-cause analysis.

Dependency-aware impact analysis.

Corrective recommendations with supporting evidence.

ArchLens-specific benchmark and annotation specification.

Baseline and ablation results.

Error analysis and limitations.

Reproducible code, experiment configuration and documentation.

Research paper/report and final demonstration.

# 16. Research Contribution Statement

The central contribution is not simply applying an LLM to architecture diagrams. ArchLens is designed as a multimodal, evidence-grounded conformance pipeline that connects intended architecture extracted from diagrams with architecture recovered from source code, then combines deterministic graph analysis with Git evidence and LLM reasoning for root-cause and impact analysis. The project therefore evaluates the value of each evidence source through explicit baselines and ablations.

# 17. Recommended Implementation Order

1. Build the graph schemas and dataset format first.

2. Make source-code dependency extraction deterministic and testable.

3. Build a minimal diagram-to-graph baseline before adding complex VLM prompting.

4. Implement explicit conformance rules before LLM-based explanations.

5. Add Git evidence only after violation localization is stable.

6. Add LLM RCA and recommendations over filtered evidence rather than whole repositories.

7. Run baselines and ablations before polishing the dashboard.

8. Freeze the benchmark/test set before final evaluation.

ArchLens — 50-Day Scrum Implementation Document